## FFY 2022-23 Oct 31
MTC FFY 2022-23 Annual Obligation Plan | [43 empty] | Remarks | Field Review (mm/dd/yy) | RFA Submission (EDS or Actual) (mm/dd/yy) | TIP Prog Year | Conf in Plan
Project List | [20 empty] | Remaining | 111592498 | 72790575 | 184383073 |  | Obligations |  |  |  |  | Total |  | 111592498 | 72790575 | 184383073 |  | Fund Type |  |  |  |  | Total | Remaining | [7 empty] | Total
2022-10-31 | [12 empty] | CTC Allocation |  | Obligation | [5 empty] | Balance | STP | CMAQ | STP/CMAQ | HSIP | HBP | RTIP | ATP | SB1 | Other-Fed | Obligations |  | STP | CMAQ | STP/CMAQ | HSIP | HBP | RTIP | ATP | SB1 | OTHER-FED | Programmed | Balance | Enter comments or additional information. Provide contact names & phone numbers or email addresses for questions. | [6 empty] | Programmed
County | Local Agency | TIP ID | FMS ID | Unique ID | Program | Fund Source | FPN | FPN | FPN | FPN | Phase | Project Title | Latest Action | CTC Allocation | Latest Action | Latest Action | Planned | Planned or | Planned | Oblig/Alloc | 98.8% | 0% | 0.1769% | 0.06985% | 0% | 12.11% | 0% | 0% | 0% | 0% | 1.198% | Oblig | 37.64% | 19.67% | 57.31% | 2.292% | 12.7% | 9.566% | 9.946% | 0% | 8.188% | 100% | 98.8% | [5 empty] | Dated Added | Entered in | 100%
[13 empty] | Status | Date | Status | Date | Award | Field Review | Oblig | Deadline | 320192200.0221 | 0 | 128788 | 128788 | 0 | 3753672 | 0 | 0 | 0 | 0 | 3882460 | Date | 121983874 | 63735710 | 185719584 | 7426700 | 41158245.4821 | 31001238 | 32234000 | 0 | 26534892.54 | 324074660.0221 | 320192200.0221 | [5 empty] | to Plan | FMS | 324074660.0221
County | Sponsor | TIP ID | FMS ID | Unique ID | Program | Fund Source | Prefix | LoCode | Proj # | FPN | Phase | Project Title | Latest Action | CTC Allocation | Latest Action | Action Date | Planned Award | Field Review | Planned Oblig | Deadline | Balance | STP | CMAQ | STP/CMAQ | HSIP | Seismic | RTIP | ATP | SB1 | EARMARK/CRRSAA | Oblig Amount | Oblig Date | STP | CMAQ | STP/CMAQ | HSIP | Seismic | STIP | ATP | SB1 | EARMARK/CRRSAA | Total | Balance | Remarks | Field Review | RFA | Prog Year | Resp'd? | Dated Added | DATE | Total
Alameda | ACTC | ALA110033 | 5013 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP | STPCMLNI | 6080 | 013 | STPCMLNI-6080(013) | CON | Alameda County Safe Routes to School | Ext to 12/31/21 | 2021-12-31 |  |  | N/A |  | 2022-09-12 | 2023-09-30 | 1500000 |  |  | 0 | [6 empty] | 0 |  | 1500000 |  | 1500000 | [6 empty] | 1500000 | 1500000 | [5 empty] | 2022-10-01 |  | 1500000
Alameda | ACTC | ALA210022 | 7261 | EARMARK-T5-RE | EARMARK | EARMARK |  | 6480 |  | -6480() | CON | Alameda County Rail Safety Enhancement Program | [7 empty] | 2024-09-01 | 598 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 598 | 598 | 598 | [5 empty] | 2022-10-01 |  | 598
Alameda | Alameda | ALA170049 | 6539 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5014 | 047 | -5014(047) | CON | Central Avenue Safety Improvements |  |  | NEPA Clearance | 2021-11-30 | 2023-06-30 | PID 4/20 | 2022-11-30 | 2023-01-31 | 2000000 |  |  | 0 | [6 empty] | 0 |  | 2000000 |  | 2000000 | [6 empty] | 2000000 | 2000000 | [5 empty] | 2022-10-01 |  | 2000000
Alameda | Alameda | ALA170049 | 6539 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ |  | 5014 | 047 | -5014(047) | CON | Central Avenue Safety Improvements |  |  | NEPA Clearance | 2021-11-30 | 2023-06-30 | PID 4/20 | 2022-11-30 | 2023-01-31 | 1487000 |  |  | 0 | [6 empty] | 0 |  |  | 1487000 | 1487000 | [6 empty] | 1487000 | 1487000 | [5 empty] | 2022-10-01 |  | 1487000
Alameda | Alameda | ALA170049 | 6539 | ATP-ST-T5-3-FED | ATP-ST | ATP-FED |  | 5014 | 047 | -5014(047) | CON | Central Avenue Safety Improvements |  |  | NEPA Clearance | 2021-11-30 | 2023-06-30 | PID 4/20 | 2022-11-30 | 2023-01-31 | 6846000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 6846000 |  |  | 6846000 | 6846000 | [5 empty] | 2022-10-01 |  | 6846000
Alameda | Alameda | ALA170073 | 6758 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5014 | 046 | -5014(046) | CON | Clement Avenue Complete Streets |  |  | NEPA Clearance | 2022-10-31 | 2023-02-28 | 2018-08-08 | 2022-10-31 | 2023-01-31 | 2000000 |  |  | 0 | [6 empty] | 0 |  | 2000000 |  | 2000000 | [6 empty] | 2000000 | 2000000 | [5 empty] | 2022-10-01 |  | 2000000
Alameda | Alameda | ALA170073 | 6758 | STP-T5-OBAG2-CO | OBAG 2 | CMAQ |  | 5014 | 046 | -5014(046) | CON | Clement Avenue Complete Streets |  |  | NEPA Clearance | 2022-10-31 | 2023-02-28 | 2018-08-08 | 2022-10-31 | 2023-01-31 | 2451000 |  |  | 0 | [6 empty] | 0 |  |  | 2451000 | 2451000 | [6 empty] | 2451000 | 2451000 | [5 empty] | 2022-10-01 |  | 2451000
Alameda | Alameda County | VAR170002 | 6989 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5933 | 152 | HSIPL-5933(152) | CON | Alameda Co Unsignalized Intersection ImpsH9-04-001 |  |  | Ext. to 6/30/23 | 2022-07-08 | 2023-11-01 | 2021-03-21 | 2023-06-01 | 2023-06-30 | 1750000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 1750000 | [5 empty] | 1750000 | 1750000 | 7/8 - 12-month Ext was approved by Caltrans 3/11 - Working on ext request to FFY23 (June 23)- Data collection and analysis affected by COVID, right-of-way acquisitions issues 8/31/21 - The County requested an extension to 9/30/22. Awaiting CT confirmation. |  |  |  |  | 2021-09-30 |  | 1750000
Alameda | Alameda County | VAR170002 | 6990 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5933 | 153 | HSIPL-5933(153) | CON | Alameda Co-Signalized Intersection Imps H9-04-002 |  |  | Ext. to 6/30/23 | 2022-07-08 | 2023-11-01 | 2021-03-21 | 2023-06-01 | 2023-06-30 | 2293900 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 2293900 | [5 empty] | 2293900 | 2293900 | 7/8 - 12-month Ext was approved by Caltrans 3/11 - Working on ext request to FFY23 (June 23)- Utility relocations, acquiring needed right-of-way for signal equipment, ADA compliance, etc. issues 8/31/21 - The County requested an extension to 9/30/22. Awaiting CT confirmation. |  |  |  |  | 2021-09-30 |  | 2293900
Alameda | Alameda County | VAR170002 | 6988 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5933 | 154 | HSIPL-5933(154) | CON | H9-04-003 Alameda County Rural Roads Safety Imps |  |  | Ext. to 12/31/22 | 2022-07-08 | 2023-02-01 | 2021-06-10 | 2022-09-30 | 2022-12-31 | 1330000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 1330000 | [5 empty] | 1330000 | 1330000 | 7/8 - 6-month Ext was approved by Caltrans 3/11 - Working on ext request to FFY23 (Dec 22) - Long utility relocations process (utility agreements, relocation design, etc.), construction in environmentally sensitive areas issues 8/31/21 - The County requested an extension to 9/30/22. Awaiting CT confirmation. |  |  |  |  | 2021-09-30 |  | 1330000
Alameda | Albany | ALA170088 | 6743 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5178 | 016 | -5178(016) | CON | San Pablo Ave and Buchanan St Pedestrian Imps. |  |  | NEPA Cat-Ex validated | 2022-06-14 | 2023-03-01 | 2021-05-03 | 2022-09-30 | 2023-01-31 | 340000 |  |  | 0 | [6 empty] | 0 |  | 340000 |  | 340000 | [6 empty] | 340000 | 340000 | [5 empty] | 2022-10-01 |  | 340000
Alameda | Berkeley | ALA170067 | 6738 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5057 | 051 | -5057(051) | CON | Southside Complete Streets and Transit Improvement |  |  | NEPA Clearance | 2022-11-07 | 2023-05-23 | 2019-04-19 | 2022-11-10 | 2023-01-31 | 3677000 |  |  | 0 | [6 empty] | 0 |  | 3677000 |  | 3677000 | [6 empty] | 3677000 | 3677000 | [5 empty] | 2022-10-01 |  | 3677000
Alameda | Berkeley | ALA170067 | 6738 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ |  | 5057 | 051 | -5057(051) | CON | Southside Complete Streets and Transit Improvement |  |  | NEPA Clearance | 2022-11-07 | 2023-05-23 | 2019-04-19 | 2022-11-10 | 2023-01-31 | 3658000 |  |  | 0 | [6 empty] | 0 |  |  | 3658000 | 3658000 | [6 empty] | 3658000 | 3658000 | [5 empty] | 2022-10-01 |  | 3658000
Alameda | Caltrans | ALA170060 | 6785 | CMAQ-T4-2-FPI-REG-CT | OBAG | CMAQ |  | 6204 |  | -6204() | CON | GL: Alameda and Marin Counties - TOS-Mobility | [7 empty] | 2023-01-31 | 20000 |  |  | 0 | [6 empty] | 0 |  |  | 20000 | 20000 | [6 empty] | 20000 | 20000 | [5 empty] | 2022-10-01 |  | 20000
Alameda | Caltrans | ALA170060 | 6785 | CMAQ-T4-2-FPI-REG-CT | OBAG | CMAQ |  | 6204 |  | -6204() | CON | GL: Alameda and Marin Counties - TOS-Mobility | [7 empty] | 2023-01-31 | 270000 |  |  | 0 | [6 empty] | 0 |  |  | 270000 | 270000 | [6 empty] | 270000 | 270000 | [5 empty] | 2022-10-01 |  | 270000
Alameda | Caltrans | ALA170060 | 6785 | CMAQ-T4-2-FPI-REG-CT | OBAG | CMAQ |  | 6204 |  | -6204() | CON | GL: Alameda and Marin Counties - TOS-Mobility | [7 empty] | 2023-01-31 | 3978255 |  |  | 0 | [6 empty] | 0 |  |  | 3978255 | 3978255 | [6 empty] | 3978255 | 3978255 | [5 empty] | 2022-10-01 |  | 3978255
Alameda | CCJPA | ALA210033 | 7355 | STP-T5-OBAG2-REG-RSI | OBAG 2 | STP |  |  |  | -() | PE | CCJPA SR84 Intermodal Bus Facility | [7 empty] | 2023-01-31 | 100000 |  |  | 0 | [6 empty] | 0 |  | 100000 |  | 100000 | [6 empty] | 100000 | 100000 | [5 empty] | 2022-10-01 |  | 100000
Alameda | Hayward | ALA170066 | 6737 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5050 | 047 | STPL-5050(047) | CON | Winton Ave Complete Street |  |  | RFA at CT-HQ | 2022-05-17 | 2021-12-28 | 2020-06-23 | 2022-02-28 | 2021-01-31 | 1662000 |  |  | 0 | [6 empty] | 0 |  | 1662000 |  | 1662000 | [6 empty] | 1662000 | 1662000 | 9/1 -  When I submitted the $620K and matching funds for the TIP, Adam said that the funds had to be in 23-24 because there is no earlier capacity. We plan to request the $620K as EPSP during 22-23. 8/31 - These funds have been reprogrammed to SR2S, ALA110033; $620K of which will be obligated in 22-23 with $1.5M SSM SR2S. 3/11 - Funds may need to be reprogrammed to another project due to propsed Caltrans I-880. W Winton I/C project. 9/15/21 - Follow up on Inactive Obligations 8/30/21 - City missed FFY20/21 deadline and must follow-up on Inactives 3/2 - Jacki requested status on 2/26 8/28 - Confirmed for FFY20/21 |  |  |  |  | 2020-09-30 |  | 1662000
Alameda | MTC | ALA190018 | 6963 | STP-CRRSAA | OBAG 2 | CRRSAA+ |  | 6084 |  | -6084() | CON | Bay Bridge Forward: Alameda I-580 WB HOV Lane Ext | [7 empty] | 2023-09-30 | 7000000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 7000000 | 7000000 | 7000000 | [5 empty] | 2021-09-30 |  | 7000000
Alameda | MTC | ALA170057 | 6720 | CMAQ-T5-OBAG2-REG-AOM | OBAG 2 | CMAQ |  | 6084 | 220 | -6084(220) | CON | I-880 Integrated Corridor Management - Central | [7 empty] | 2023-01-31 | 1498000 |  |  | 0 | [6 empty] | 0 |  |  | 1498000 | 1498000 | [6 empty] | 1498000 | 1498000 | [5 empty] | 2022-10-01 |  | 1498000
Alameda | Oakland | VAR170002 | 6977 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5012 | 158 | HSIPL-5012(158) | CON | Oakland - Various Intersection Imprvmnts H9-04-022 |  |  |  |  | 2022-01-31 | 2019-06-18 | 2022-12-01 | 2022-12-31 | 250000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 250000 | [5 empty] | 250000 | 250000 | [5 empty] | 2021-09-30 |  | 250000
Alameda | Oakland | VAR170012 | 5221 | 33C0215 | HBP-Seismic | Bridge | STPLZ | 5012 | 124 | STPLZ-5012(124) | CON | Leimert Blvd over Sausal Creek |  |  | Partially Obligated | 2022-06-28 | 2022-03-31 | 2017-06-01 | 2021-09-30 | 2021-04-30 | 3746328 |  |  | 0 |  | 3753672 |  |  |  |  | 3753672 |  |  |  | 0 |  | 7500000 |  |  |  |  | 7500000 | 3746328 | 3/5 - Executed PDA states RFA CON in April 21 |  |  |  |  | 2021-03-05 | 2022-06-30 | 7500000
Alameda | San Leandro | ALA170075 | 6765 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5041 | 048 | STPL-5041(048) | CON | San Leandro Washington Avenue Rehabilitation |  |  | NEPA Clearance | 2022-08-02 | 2023-02-28 | 2018-11-07 | 2022-11-30 | 2023-01-31 | 975000 |  |  | 0 | [6 empty] | 0 |  | 975000 |  | 975000 | [6 empty] | 975000 | 975000 | [5 empty] | 2022-10-01 |  | 975000
Contra Costa | Antioch | CC-170035 | 6711 | CMAQ-T5-OBAG2-CO-SRTS | OBAG 2 | CMAQ | CML | 5038 | 025 | CML-5038(025) | CON | Antioch - L Street Pathway to Transit |  |  | NEPA Review at CT | 2022-09-06 | 2023-01-30 | 2021-06-29 | 2022-11-16 | 2023-01-31 | 1469000 |  |  | 0 | [6 empty] | 0 |  |  | 1469000 | 1469000 | [6 empty] | 1469000 | 1469000 | [5 empty] | 2022-10-01 |  | 1469000
Contra Costa | CCTA | CC-210012 | 7317 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP | STPLNI | 6072 | 032 | STPLNI-6072(032) | OTHER | East Bay Integrated Transit Plan |  |  | RFA at CT-HQ | 2022-09-06 | 2022-12-01 | N/A - NI | 2022-09-30 | 2023-09-30 | 500000 |  |  | 0 | [6 empty] | 0 |  | 500000 |  | 500000 | [6 empty] | 500000 | 500000 | 8/30/21 - CCTA will work with MTC staff to see if the Study can be funded through FTA and therefore not have to go to DLAE. FTA transfer will be completed before 9/30/22. |  |  |  |  | 2021-09-30 |  | 500000
Contra Costa | Clayton | CC-170047 | 6762 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5386 | 011 | STPL-5386(011) | CON | Clayton Neighborhood Street Rehab |  |  | NEPA | 2022-10-01 | 2023-03-01 | 2022-07-22 | 2022-11-01 | 2023-01-31 | 308000 |  |  | 0 | [6 empty] | 0 |  | 308000 |  | 308000 | [6 empty] | 308000 | 308000 | [5 empty] | 2022-10-01 |  | 308000
Contra Costa | Concord | CC-210003 | 7232 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 5135 |  | -5135() | CON | East Downtown Concord PDA Access and SR2T |  |  | NEPA | 2022-09-30 | 2023-01-01 | 2021-10-21 | 2022-11-30 | 2023-09-30 | 2164000 |  |  | 0 | [6 empty] | 0 |  | 2164000 |  | 2164000 | [6 empty] | 2164000 | 2164000 | 3/14 - City still needs to obtain NEPA clearance (est. 6/30) and ROW cert (est. 7/15% |  |  |  |  | 2021-09-30 |  | 2164000
Contra Costa | Concord | CC-170037 | 6714 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5135 |  | -5135() | CON | Concord Willow Pass Road Repaving SR2T |  |  | NEPA | 2021-08-13 |  | 2019-06-21 | 2022-11-30 | 2023-01-31 | 4183000 |  |  | 0 | [6 empty] | 0 |  | 4183000 |  | 4183000 | [6 empty] | 4183000 | 4183000 | [5 empty] | 2022-10-01 |  | 4183000
Contra Costa | Concord | CC-170037 | 6714 | CMAQ-T4-2-RSRTS-REG | OBAG | CMAQ |  | 5135 |  | -5135() | CON | Concord Willow Pass Road Repaving SR2T |  |  | NEPA | 2021-08-13 |  | 2019-06-21 | 2022-11-30 | 2023-01-31 | 215000 |  |  | 0 | [6 empty] | 0 |  |  | 215000 | 215000 | [6 empty] | 215000 | 215000 | [5 empty] | 2022-10-01 |  | 215000
Contra Costa | Concord | CC-170037 | 6714 | CMAQ-T5-OBAG2-CO-SRTS | OBAG 2 | CMAQ |  | 5135 |  | -5135() | CON | Concord Willow Pass Road Repaving SR2T |  |  | NEPA | 2021-08-13 |  | 2019-06-21 | 2022-11-30 | 2023-01-31 | 1012000 |  |  | 0 | [6 empty] | 0 |  |  | 1012000 | 1012000 | [6 empty] | 1012000 | 1012000 | [5 empty] | 2022-10-01 |  | 1012000
Contra Costa | Danville | CC-170058 | 6715 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5434 | 026 | STPL-5434(026) | CON | Camino Ramon Improvements |  |  | AC Authorized at FHWA | 2022-09-23 | 2022-12-01 | 2021-08-26 | 2022-09-01 | 2023-01-31 | 1357000 |  |  | 0 | [6 empty] | 0 |  | 1357000 |  | 1357000 | [6 empty] | 1357000 | 1357000 | 9/15/21 - Follow with City on Inactive Obligation |  |  |  |  | 2021-09-30 |  | 1357000
Contra Costa | Danville | CC-170001 | 6343 | STP-T4-2-OBAG | OBAG | STP | STPL | 5434 | 027 | STPL-5434(027) | CON | San Ramon Valley Blvd Slurry Seal and Striping |  |  | NEPA | 2022-03-14 | 2022-12-15 | 2021-10-04 | 2022-10-15 | 2023-01-31 | 1475000 |  |  | 0 | [6 empty] | 0 |  | 1475000 |  | 1475000 | [6 empty] | 1475000 | 1475000 | 9/15/21 - Follow with City on Inactive Obligation |  |  |  |  | 2021-09-15 |  | 1475000
Contra Costa | Danville | CC-170001 | 6343 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5434 | 027 | STPL-5434(027) | CON | San Ramon Valley Blvd Slurry Seal and Striping |  |  | NEPA | 2022-03-14 | 2022-12-15 | 2021-10-04 | 2022-10-15 | 2023-01-31 | 130000 |  |  | 0 | [6 empty] | 0 |  | 130000 |  | 130000 | [6 empty] | 130000 | 130000 | [5 empty] | 2022-10-01 |  | 130000
Contra Costa | El Cerrito | CC-070046 | 918 | STP-T5-OBAG2-CO | OBAG 2 | STP | CML | 5239 | 029 | CML-5239(029) | CON | El Cerrito del Norte Area TOD Complete Street Imps |  |  | NEPA | 2022-03-01 | 2023-04-15 | N/A - CT ROW | 2022-12-01 | 2023-01-31 | 120000 |  |  | 0 | [6 empty] | 0 |  | 120000 |  | 120000 | [6 empty] | 120000 | 120000 | [5 empty] | 2022-10-01 |  | 120000
Contra Costa | El Cerrito | CC-070046 | 918 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ | CML | 5239 | 029 | CML-5239(029) | CON | El Cerrito del Norte Area TOD Complete Street Imps |  |  | NEPA | 2022-03-01 | 2023-04-15 | N/A - CT ROW | 2022-12-01 | 2023-01-31 | 4841000 |  |  | 0 | [6 empty] | 0 |  |  | 4841000 | 4841000 | [6 empty] | 4841000 | 4841000 | [5 empty] | 2022-10-01 |  | 4841000
Contra Costa | Martinez | CC-170059 | 6753 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5024 | 028 | STPL-5024(028) | CON | Alhambra Avenue Downtown Resurfacing |  |  | NEPA | 2022-08-01 | 2023-03-15 | 2022-05-01 | 2022-11-01 | 2023-01-31 | 846000 |  |  | 0 | [6 empty] | 0 |  | 846000 |  | 846000 | [6 empty] | 846000 | 846000 | [5 empty] | 2022-10-01 |  | 846000
Contra Costa | Pittsburg | CC-170042 | 6733 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5127 | 041 | STPL-5127(041) | CON | City of Pittsburg Pavement Improvements |  |  | NEPA | 2021-10-11 |  | 2021-08-03 | 2022-12-01 | 2023-01-31 | 2410000 |  |  | 0 | [6 empty] | 0 |  | 2410000 |  | 2410000 | [6 empty] | 2410000 | 2410000 | [5 empty] | 2021-09-30 |  | 2410000
Contra Costa | Pittsburg | CC-170040 | 6731 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ | CML | 5127 | 036 | CML-5127(036) | PE | Pittsburg BART Pedestrian and Bicycle Connectivity |  |  | NEPA | 2020-08-13 |  | 2018-10-24 | 2022-10-01 | 2023-01-31 | 120000 |  |  | 0 | [6 empty] | 0 |  |  | 120000 | 120000 | [6 empty] | 120000 | 120000 | [5 empty] | 2022-10-01 |  | 120000
Contra Costa | Pittsburg | CC-170040 | 6731 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ | CML | 5127 | 036 | CML-5127(036) | CON | Pittsburg BART Pedestrian and Bicycle Connectivity |  |  | NEPA | 2020-08-13 |  | 2018-10-24 | 2022-10-01 | 2023-01-31 | 3267000 |  |  | 0 | [6 empty] | 0 |  |  | 3267000 | 3267000 | [6 empty] | 3267000 | 3267000 | [5 empty] | 2022-10-01 |  | 3267000
Contra Costa | Richmond | CC-210007 | 7283 | STP-CRRSAA | OBAG 2 | CRRSAA+ | STPL | 5137 | 056 | STPL-5137(056) | CON | Richmond 13th Street Complete Streets Imps |  |  | NEPA | 2021-12-30 | 2023-05-01 | 2021-12-29 | 2022-11-30 | 2023-09-30 | 2821000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 2821000 | 2821000 | 2821000 | [5 empty] | 2021-09-30 |  | 2821000
Contra Costa | Richmond | CC-170056 | 6708 | CMAQ-T5-OBAG2-CO-SRTS | OBAG 2 | CMAQ | CML | 5137 | 055 | CML-5137(055) | CON | Lincoln Elementary SRTS Pedestrian Enhancements |  |  | NEPA | 2022-08-15 | 2023-04-30 | 2021-04-06 | 2022-11-30 | 2023-01-31 | 497000 |  |  | 0 | [6 empty] | 0 |  |  | 497000 | 497000 | [6 empty] | 497000 | 497000 | [5 empty] | 2022-10-01 |  | 497000
Contra Costa | San Pablo | CC-170031 | 6679 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP | STPL | 5303 | 022 | STPL-5303(022) | PE | Giant Road Cycletrack & Pavement Rehabilitation |  |  | NEPA | 2022-08-30 | 2022-11-30 | 2021-12-07 | 2022-10-30 | 2023-09-30 | 50000 |  |  | 0 | [6 empty] | 0 |  | 50000 |  | 50000 | [6 empty] | 50000 | 50000 | 9/16/21 - The STP funded the original pavement rehab project. Quick Strick funds programmed for Cycle track. Projects are now combined as one project. |  |  |  |  | 2021-09-30 |  | 50000
Contra Costa | San Pablo | CC-170031 | 6679 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP | STPL | 5303 | 022 | STPL-5303(022) | CON | Giant Road Cycletrack & Pavement Rehabilitation |  |  | NEPA | 2022-08-30 | 2022-11-30 | 2021-12-07 | 2022-10-30 | 2023-09-30 | 650000 |  |  | 0 | [6 empty] | 0 |  | 650000 |  | 650000 | [6 empty] | 650000 | 650000 | [5 empty] | 2021-09-30 |  | 650000
Contra Costa | San Pablo | CC-170031 | 6679 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5303 | 022 | STPL-5303(022) | CON | Giant Road Cycletrack & Pavement Rehabilitation |  |  | NEPA | 2022-08-30 | 2022-11-30 | 2021-12-07 | 2022-10-30 | 2023-01-31 | 618000 |  |  | 0 | [6 empty] | 0 |  | 618000 |  | 618000 | [6 empty] | 618000 | 618000 | 9/16/21 - The STP funded the original pavement rehab project. Quick Strick funds programmed for Cycle track. Projects are now combined as one project. 9/15/21 - Request to add back on AOP. Missed FFY20-21 AOP 8/30/21 - Request to move to FY22/23 Archeological study may prevent obligation til FY21/22 |  |  |  |  | 2020-09-30 |  | 618000
Contra Costa | San Ramon | CC-170014 | 6516 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ | CML | 5437 | 030 | CML-5437(030) | CON | Iron Horse Trail Bike and Pedestrian Overcrossing |  |  | NEPA | 2020-04-03 | 2022-10-31 | 2019-09-12 | 2022-10-31 | 2023-01-31 | 4840000 |  |  | 0 | [6 empty] | 0 |  |  | 4840000 | 4840000 | [6 empty] | 4840000 | 4840000 | [5 empty] | 2022-10-01 |  | 4840000
Contra Costa | San Ramon | CC-210013 | 7313 | CMAQ-T5-OBAG2-REG-CI | OBAG 2 | CMAQ | CML | 5437 | 033 | CML-5437(033) | CON | San Ramon Transit Center - Shared Mobility Hub |  |  | NEPA | 2022-09-12 | 2023-04-30 | 2022-08-12 | 2022-12-12 | 2023-01-31 | 387600 |  |  | 0 | [6 empty] | 0 |  |  | 387600 | 387600 | [6 empty] | 387600 | 387600 | [5 empty] | 2022-10-01 |  | 387600
Marin | GGBHTD | MRN050018 | 1391 | EARMARK-T3-HPP | EARMARK | EARMARK | RPSTPL | 6003 | 010 | RPSTPL-6003(010) | CON | Golden Gate Bridge Seismic Retrofit, Phase 3B | [7 empty] | 2022-01-31 | 1430620.54 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 1430620.54 | 1430620.54 | 1430620.54 | 8/18 - GGB will submit a TIP revision In Nov/Dec to move partial funds to MRN050018. |  |  |  |  | 2021-09-30 |  | 1430620.54
Marin | Larkspur | MRN190011 | 6944 | CMAQ-T5-OBAG2-REG-RSI | OBAG 2 | CMAQ | CML | 5166 | 027 | CML-5166(027) | CON | Old Redwood Highway Multi-Use Path |  |  | RFA at CT-HQ | 2022-09-15 | 2023-03-01 | 2021-10-14 | 2022-09-01 | 2023-01-31 | 1120000 |  |  | 0 | [6 empty] | 0 |  |  | 1120000 | 1120000 | [6 empty] | 1120000 | 1120000 | [5 empty] | 2022-10-01 |  | 1120000
Marin | Marin County | VAR170002 | 6968 | H9-04-017 | HSIP 9 | HSIP | HSIPL | 5927 | 123 | HSIPL-5927(123) | CON | Marin Co-Upgrade Non-Standard Guardrails H9-04-017 |  |  |  |  | Spring 2023 | 2019-06-04 | 2022-12-01 | 2022-12-31 | 861200 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 861200 | [5 empty] | 861200 | 861200 | 9/1 - Project confirmed for FFY20/21. 6/6 - Deadline 6/30/22? |  |  |  |  | 2020-09-30 |  | 861200
Marin | Marin County | MRN170027 | 6524 | STP-T5-OBAG2-REG-PCA | OBAG 2 | STP | STPL | 5927 | 130 | STPL-5927(130) | CON | Hicks Valley/MarshallPetaluma/Wilson Hill Rd Rehab |  |  | NEPA Approval | 2022-05-25 | 2022-04-30 | 2021-09-24 | 2022-12-01 | 2023-01-31 | 1181000 |  |  | 0 | [6 empty] | 0 |  | 1181000 |  | 1181000 | [6 empty] | 1181000 | 1181000 | [5 empty] | 2022-10-01 |  | 1181000
Marin | MCTD | MRN210002 | 7197 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP | FTASTPL | 6343 | 006 | FTASTPL-6343(006) | PE | MCTD - Bus Stop Improvements | [7 empty] | 2023-09-30 | 80000 |  |  | 0 | [6 empty] | 0 |  | 80000 |  | 80000 | [6 empty] | 80000 | 80000 | 8/2 - MCTD submitted FTA transfer request |  |  |  |  | 2021-09-30 |  | 80000
Marin | Novato | VAR170002 | 7001 | HSIP-T5-9 | HSIP 9 | HSIP | HSIPL | 5361 | 031 | HSIPL-5361(031) | CON | Novato Traffic, Bicycle & Pedestrian Improvements |  |  | Ext to 6/30/23 | 2022-03-14 | 2022-12-26 | 2021-08-16 | 2022-11-15 | 2023-06-30 | 941600 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | 941600 | [5 empty] | 941600 | 941600 | [5 empty] | 2021-09-30 |  | 941600
Napa | MTC | NAP190007 | 7162 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 6084 |  | -6084() | CON | Napa Valley Forward: Safety & Operational Impv | [7 empty] | 2023-09-30 | 4300000 |  |  | 0 | [6 empty] | 0 |  | 4300000 |  | 4300000 | [6 empty] | 4300000 | 4300000 | [5 empty] | 2021-09-30 |  | 4300000
Region | MTC | REG090003 | 4271 | CMAQ-T4-2-FPI-REG | OBAG | CMAQ |  | 6084 |  | -6084() | CON | Freeway Performance Initiative (FPI) | [7 empty] | 2023-01-31 | 402152 |  |  | 0 | [6 empty] | 0 |  |  | 402152 | 402152 | [6 empty] | 402152 | 402152 | [5 empty] | 2022-10-01 |  | 402152
Region | MTC | REG170002 | 6316 | STP-T5-OBAG2-REG-AOM | OBAG 2 | STP |  | 6084 |  | -6084() | PE | Connected Bay Area | [7 empty] | 2023-01-31 | 3000000 |  |  | 0 | [6 empty] | 0 |  | 3000000 |  | 3000000 | [6 empty] | 3000000 | 3000000 | [5 empty] | 2022-10-01 |  | 3000000
Region | MTC | REG170002 | 6316 | STP-T5-OBAG2-REG-AOM | OBAG 2 | STP |  | 6084 |  | -6084() | CON | Connected Bay Area | [7 empty] | 2023-01-31 | 1600000 |  |  | 0 | [6 empty] | 0 |  | 1600000 |  | 1600000 | [6 empty] | 1600000 | 1600000 | [5 empty] | 2022-10-01 |  | 1600000
Region | MTC | REG170002 | 6316 | STP-T5-OBAG2-REG-AOM | OBAG 2 | STP |  | 6084 |  | -6084() | CON | Connected Bay Area | [7 empty] | 2023-01-31 | 6000000 |  |  | 0 | [6 empty] | 0 |  | 6000000 |  | 6000000 | [6 empty] | 6000000 | 6000000 | [5 empty] | 2022-10-01 |  | 6000000
Region | MTC | REG170013 | 6739 | STP-T5-OBAG2-REG-AOM | OBAG 2 | STP |  | 6084 |  | -6084() | CON | 511 Next Gen | [7 empty] | 2023-01-31 | 5372000 |  |  | 0 | [6 empty] | 0 |  | 5372000 |  | 5372000 | [6 empty] | 5372000 | 5372000 | [5 empty] | 2022-10-01 |  | 5372000
Region | MTC | REG170022 | 6833 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 6084 |  | -6084() | CON | Clipper 2.0 Fare Payment System | [7 empty] | 2023-09-30 | 900000 |  |  | 0 | [6 empty] | 0 |  | 900000 |  | 900000 | [6 empty] | 900000 | 900000 | [5 empty] | 2022-10-01 |  | 900000
Region | MTC | REG170023 | 6730 | STP-T5-OBAG2-REG-AOM | OBAG 2 | STP | STPL | 6084 | 291 | STPL-6084(291) | PE | Freeway Performance Program: SR-84 |  |  | RFA at CT-HQ | 2022-10-05 |  |  |  | 2023-01-31 | 4000000 |  |  | 0 | [6 empty] | 0 |  | 4000000 |  | 4000000 | [6 empty] | 4000000 | 4000000 | [5 empty] | 2022-10-06 |  | 4000000
Region | MTC | Various |  | STP-T6-OBAG3-CO | OBAG 3 | STP |  | 6084 |  | -6084() | OTHER | Regional Planning Activities and PPM - CTAs | [7 empty] | 2023-01-31 | 21612000 |  |  | 0 | [6 empty] | 0 |  | 21612000 |  | 21612000 | [6 empty] | 21612000 | 21612000 | 9/15 -MA: CTA PL augmentations |  |  |  |  | 2022-09-27 |  | 21612000
Region | MTC | Various |  | STP-T6-OBAG3-REG-CSCC | OBAG 3 | STP |  | 6084 |  | -6084() | OTHER | Regional Planning Activities and PPM - CTAs | [7 empty] | 2023-01-31 | 3000000 |  |  | 0 | [6 empty] | 0 |  | 3000000 |  | 3000000 | [6 empty] | 3000000 | 3000000 | 9/15 -MA: CTA CBTPs |  |  |  |  | 2022-09-27 |  | 3000000
Region | MTC | Various |  | STP-T6-OBAG3-REG-CSCC | OBAG 3 | STP |  | 6084 |  | -6084() | OTHER | Regional Planning Activities and PPM - CTAs | [7 empty] | 2023-01-31 | 1280000 |  |  | 0 | [6 empty] | 0 |  | 1280000 |  | 1280000 | [6 empty] | 1280000 | 1280000 | 9/15 -MA: CTA LRSPs |  |  |  |  | 2022-09-27 |  | 1280000
Region | MTC | REG210201 | 10020 | STP-T5-OBAG2-REG-PCA | OBAG 2 | STP |  | 6084 |  | -6084() | OTHER | Priority Conservation Area Grant Implementation | [7 empty] | 2023-01-31 | 525000 |  |  | 0 | [6 empty] | 0 |  | 525000 |  | 525000 | [6 empty] | 525000 | 525000 | [5 empty] | 2022-09-27 |  | 525000
Region | MTC |  | 10034 | STP-T6-OBAG3-REG-CSCC | OBAG 3 | STP |  | 6084 |  | -6084() | OTHER | Bay Trail Planning | [7 empty] | 2023-01-31 | 1500000 |  |  | 0 | [6 empty] | 0 |  | 1500000 |  | 1500000 | [6 empty] | 1500000 | 1500000 | [5 empty] | 2022-09-29 |  | 1500000
Region | MTC |  | 10034 | STP-T6-OBAG3-REG-CSCC | OBAG 3 | STP |  | 6084 |  | -6084() | OTHER | Bay Trail Technical Assistance | [7 empty] | 2023-01-31 | 250000 |  |  | 0 | [6 empty] | 0 |  | 250000 |  | 250000 | [6 empty] | 250000 | 250000 | [5 empty] | 2022-09-29 |  | 250000
Region | MTC | VAR190007 | 7092 | STP-T6-OBAG3-REG-MSOP | OBAG 3 | STP |  | 6084 |  | -6084() | CON | GL: Transit Preventive Maintenance | [7 empty] | 2023-01-31 | 7000000 |  |  | 0 | [6 empty] | 0 |  | 7000000 |  | 7000000 | [6 empty] | 7000000 | 7000000 | [5 empty] | 2022-10-07 |  | 7000000
Region | MTC | MTC050001 | 1608 | CMAQ-T6-OBAG3-REG-CCR | OBAG 3 | CMAQ |  | 6084 |  | -6084() | CON | Bay Area Commuter Benefits Program | [7 empty] | 2023-01-31 | 10000000 |  |  | 0 | [6 empty] | 0 |  |  | 10000000 | 10000000 | [6 empty] | 10000000 | 10000000 | [5 empty] | 2022-09-30 |  | 10000000
Region | MTC | REG170003 | 6331 | CMAQ-T6-OBAG3-REG-CCR | OBAG 3 | CMAQ | CMLNI | 6084 | 290 | CMLNI-6084(290) | CON | 511 Carpool and Vanpool Programs | [7 empty] | 2023-01-31 | 3400000 |  |  | 0 | [6 empty] | 0 |  |  | 3400000 | 3400000 | [6 empty] | 3400000 | 3400000 | [5 empty] | 2022-09-30 |  | 3400000
Region | MTC | REG170006 | 6400 | CMAQ-T6-OBAG3-REG-CCR | OBAG 3 | CMAQ |  | 6084 |  | -6084() | CON | Climate Initiatives Education and Outreach |  |  | RFA at CT-HQ | 2022-10-05 |  |  |  | 2023-01-31 | 1500000 |  |  | 0 | [6 empty] | 0 |  |  | 1500000 | 1500000 | [6 empty] | 1500000 | 1500000 | [5 empty] | 2002-10-06 |  | 1500000
San Francisco | BART | SF-170016 | 6727 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP | FTASTPL | 6000 | 071 | FTASTPL-6000(071) | CON | Embarcadero Stn: New North-Side Platform Elevator |  |  | FTA Transfer at CT-HQ | 2022-10-04 |  | 2022-09-30 | 2022-09-30 | 2023-09-30 | 3144302 |  |  | 0 | [6 empty] | 0 |  | 3144302 |  | 3144302 | [6 empty] | 3144302 | 3144302 | 3/11 - Risks include labor market pressures, supply chain challenges, cost of materials, challenges with site conditions, and high bid responses. |  |  |  |  | 2021-09-30 |  | 3144302
San Francisco | SFMTA | SF-170023 | 6892 | STP-T6-OBAG3-CO | OBAG 3 | STP | CMLNI | 6328 | 092 | CMLNI-6328(092) | CON | SF Safe Routes to School Non-Infrastructure |  |  |  |  | 2022-12-01 | N/A | 2022-09-30 | 2023-01-31 | 7082000 |  |  | 0 | [6 empty] | 0 |  | 7082000 |  | 7082000 | [6 empty] | 7082000 | 7082000 | [5 empty] | 2022-09-01 |  | 7082000
San Francisco | SFCTA | SF-070027 | 3741 | 01CA0006 | HBP-Seismic | Bridge | STPLZ | 6272 | 029 | STPLZ-6272(029) | CON | Hillcrest Road West of Yerba Buena Island | [7 empty] | 2022-09-30 | 2042843.2572 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 2042843.2572 |  |  |  |  | 2042843.2572 | 2042843.2572 | 8/31 - SFCTA has been working diligently to secure funding for the project in order to obligate and begin construction. However, due to a delay in securing full funding for the project, the |  |  |  |  | 2021-09-30 |  | 2042843.2572
San Francisco | SFCTA | SF-070027 | 3741 | 01CA0002 | HBP-Seismic | Bridge | STPLZ | 6272 | 026 | STPLZ-6272(026) | ROW | WB I-80 on ramp West of Yerba Buena Island | [7 empty] | 2022-09-30 | 550000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 550000 |  |  |  |  | 550000 | 550000 | 8/31 - SFCTA has been working diligently to secure funding for the project in order to obligate and begin construction. However, due to a delay in securing full funding for the project. |  |  |  |  | 2021-09-30 |  | 550000
San Francisco | SFCTA | SF-070027 | 3741 | 01CA0002 | HBP-Seismic | Bridge | STPLZ | 6272 | 026 | STPLZ-6272(026) | CON | WB I-80 on ramp West of Yerba Buena Island | [7 empty] | 2022-09-30 | 19077010.9303 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 19077010.9303 |  |  |  |  | 19077010.9303 | 19077010.9303 | 8/31 - SFCTA has been working diligently to secure funding for the project in order to obligate and begin construction. However, due to a delay in securing full funding for the project, the |  |  |  |  | 2021-09-30 |  | 19077010.9303
San Francisco | SFCTA | SF-070027 | 3741 | 01CA0003 | HBP-Seismic | Bridge | STPLZ | 6272 | 027 | STPLZ-6272(027) | ROW | EB I-80 off ramp to TI Road (2 Bridges) | [7 empty] | 2022-09-30 | 300000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 300000 |  |  |  |  | 300000 | 300000 | 8/31 - SFCTA has been working diligently to secure funding for the project in order to obligate and begin construction. However, due to a delay in securing full funding for the project, the |  |  |  |  | 2021-09-30 |  | 300000
San Francisco | SFCTA | SF-070027 | 3741 | 01CA0003 | HBP-Seismic | Bridge | STPLZ | 6272 | 027 | STPLZ-6272(027) | CON | EB I-80 off ramp to TI Road (2 Bridges) | [7 empty] | 2022-09-30 | 8460249.4289 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 8460249.4289 |  |  |  |  | 8460249.4289 | 8460249.4289 | 8/31 - SFCTA has been working diligently to secure funding for the project in order to obligate and begin construction. However, due to a delay in securing full funding for the project, the |  |  |  |  | 2021-09-30 |  | 8460249.4289
San Francisco | SFCTA | SF-070027 | 3741 | 01CA0004 | HBP-Seismic | Bridge | STPLZ | 6272 | 028 | STPLZ-6272(028) | CON | Treasure Island Road West of SFOBB | [7 empty] | 2022-09-30 | 1724961.1255 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 1724961.1255 |  |  |  |  | 1724961.1255 | 1724961.1255 | 8/31 - SFCTA has been working diligently to secure funding for the project in order to obligate and begin construction. However, due to a delay in securing full funding for the project, the |  |  |  |  | 2021-09-30 |  | 1724961.1255
San Francisco | SFCTA | SF-070027 | 3741 | 01CA0008 | HBP-Seismic | Bridge | STPLZ | 6272 | 032 | STPLZ-6272(032) | CON | Treasure Island road West of SFOBB | [7 empty] | 2022-09-30 | 505169.0061 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 505169.0061 |  |  |  |  | 505169.0061 | 505169.0061 | 8/31 - SFCTA has been working diligently to secure funding for the project in order to obligate and begin construction. However, due to a delay in securing full funding for the project, the |  |  |  |  | 2021-09-30 |  | 505169.0061
San Francisco | SFCTA | SF-070027 | 3741 | 01CA007A | HBP-Seismic | Bridge | STPLZ | 6272 | 030 | STPLZ-6272(030) | CON | Treasure Island Road West of SFOBB | [7 empty] | 2022-09-30 | 271062.3426 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 271062.3426 |  |  |  |  | 271062.3426 | 271062.3426 | 8/31 - SFCTA has been working diligently to secure funding for the project in order to obligate and begin construction. However, due to a delay in securing full funding for the project, the |  |  |  |  | 2021-09-30 |  | 271062.3426
San Francisco | SFCTA | SF-070027 | 3741 | 01CA007B | HBP-Seismic | Bridge | STPLZ | 6272 | 031 | STPLZ-6272(031) | CON | Treasure Isand Road west of SFOBB | [7 empty] | 2022-09-30 | 357315.4159 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 357315.4159 |  |  |  |  | 357315.4159 | 357315.4159 | 8/31 - SFCTA has been working diligently to secure funding for the project in order to obligate and begin construction. However, due to a delay in securing full funding for the project, the |  |  |  |  | 2021-09-30 |  | 357315.4159
San Francisco | SFCTA | SF-070027 | 3741 | 01CA0001 | HBP-Seismic | Bridge | STPLZ | 6272 | 024 | STPLZ-6272(024) | CON | WB SFOBB on ramp West of YBI | [7 empty] | 2022-09-30 | 369633.9756 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  | 369633.9756 |  |  |  |  | 369633.9756 | 369633.9756 | 8/31 - SFCTA has been working diligently to secure funding for the project in order to obligate and begin construction. However, due to a delay in securing full funding for the project, the |  |  |  |  | 2021-09-30 |  | 369633.9756
San Francisco | SFMTA | SF-210003 | 7212 | STP-CRRSAA | OBAG 2 | CRRSAA+ |  | 6328 | 098 | -6328(098) | CON | San Francisco - Folsom Streetscape |  |  |  |  | 2023-06-30 | 2021-06-01 | 2023-02-28 | 2023-09-30 | 5000000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 5000000 | 5000000 | 5000000 | 8/31/21 - anticipated to be reprogrammed to the SFCTA’s Yerba Buena Island (YBI) West Side Bridges Project once $5,000,000 in ATP Augmentation funding is approved for the Folsom project in the fall. Per Aprile’s conversation with John on August 26, we understand that the CRRSAA funds for Folsom will automatically be included in the upcoming Annual Obligation Plan as it is programmed in the TIP and must be obligated by September 30, 2022. Once the anticipated ATP Augmentation and funding exchange is approved, we will notify John so that the Annual Obligation Plan and the TIP can be updated. |  |  |  |  | 2021-09-30 |  | 5000000
San Francisco | SFMTA | SF-210003 | 7212 | ATP-REG-T5-5-FED | ATP-REG | ATP-FED |  | 6328 | 098 | -6328(098) | CON | San Francisco - Folsom Streetscape |  |  |  |  | 2023-06-30 | 2021-06-01 | 2023-02-28 | 2023-01-31 | 7040000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 7040000 |  |  | 7040000 | 7040000 | [5 empty] | 2022-10-01 |  | 7040000
San Francisco | SFMTA | SF-210003 | 7212 | RIP-COVID21-SF | RTIP | RTIP-FED |  | 6328 | 098 | -6328(098) | CON | San Francisco - Folsom Streetscape |  |  |  |  | 2023-06-30 | 2021-06-01 | 2023-02-28 | 2023-01-31 | 3043238 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 3043238 |  |  |  | 3043238 | 3043238 | [5 empty] | 2022-09-01 |  | 3043238
San Francisco | SFMTA | SF-210005 | 7334 | CMAQ-T5-OBAG2-REG-CI | OBAG 2 | CMAQ |  | 6328 |  | -6328() | CON | Transbay Terminal Mobility Hub - East Cut |  |  |  |  | 2022-11-15 | 2022-09-15 | 2022-11-01 | 2023-01-31 | 340760 |  |  | 0 | [6 empty] | 0 |  |  | 340760 | 340760 | [6 empty] | 340760 | 340760 | [5 empty] | 2022-10-01 |  | 340760
San Francisco | SFDPW | SF-130001 | 5673 | EARMARK-T5-RE | EARMARK | EARMARK |  | 5934 | 185 | -5934(185) | CON | SF- Better Market Street Transportation Elements |  |  |  |  | 2022-05-31 | 2020-07-07 | 2023-09-30 | 2023-09-30 | 70627 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 70627 | 70627 | 70627 | [5 empty] | 2022-10-01 |  | 70627
San Mateo | Brisbane | SM-170041 | 6644 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5376 | 016 | -5376(016) | CON | Crocker Trail Commuter Connectivity Upgrades |  |  | NEPA Clearance | 4/22/222 | 2023-05-01 | 2021-01-15 | 2023-01-31 | 2023-01-31 | 885000 |  |  | 0 | [6 empty] | 0 |  | 885000 |  | 885000 | [6 empty] | 885000 | 885000 | [5 empty] | 2022-10-01 |  | 885000
San Mateo | Burlingame | SM-210007 | 7292 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 5171 |  | -5171() | CON | Burlingame Ped Safe Routes and Mobility Imp |  |  |  |  | 2022-11-01 | 2022-04-01 | 2022-09-01 | 2023-09-30 | 200000 |  |  | 0 | [6 empty] | 0 |  | 200000 |  | 200000 | [6 empty] | 200000 | 200000 | 8/22 - Spoke to Matt and project will not make FFY22 deadline and will deliver by 9/30/22 8/31/21 - Will be included in TIP after conformity grace period. |  |  |  |  | 2021-09-30 |  | 200000
San Mateo | Burlingame | SM-210009 | 7311 | CMAQ-T5-OBAG2-REG-CI | OBAG 2 | CMAQ |  | 5171 |  | -5171() | CON | Burlingame Square Caltrain Station Mobility Hub | [7 empty] | 2023-01-31 | 500000 |  |  | 0 | [6 empty] | 0 |  |  | 500000 | 500000 | [6 empty] | 500000 | 500000 | 8/22 - Spoke to Matt and project will not be delivered in FF23. Waiting for OBAG 2 extension to move out. |  |  |  |  | 2022-10-01 |  | 500000
San Mateo | Daly City | SM-210012 | 7312 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5196 | 044 | -5196(044) | CON | Southgate Ave and School St Safety Improvements |  |  | NEPA Clearance | 2022-07-26 | 2022-11-28 | 2022-03-29 | 2022-10-03 | 2023-01-31 | 450000 |  |  | 0 | [6 empty] | 0 |  | 450000 |  | 450000 | [6 empty] | 450000 | 450000 | [5 empty] | 2022-10-01 |  | 450000
San Mateo | Half Moon Bay | SM-170013 | 6626 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ |  | 5357 | 011 | -5357(011) | CON | Half Moon Bay - Poplar Complete Streets |  |  | NEPA Clearance | 2021-09-24 | 2023-05-01 | 2020-05-27 | 2023-01-31 | 2023-01-31 | 1202000 |  |  | 0 | [6 empty] | 0 |  |  | 1202000 | 1202000 | [6 empty] | 1202000 | 1202000 | [5 empty] | 2022-10-01 |  | 1202000
San Mateo | Millbrae | SM-210010 | 7314 | CMAQ-T5-OBAG2-REG-CI | OBAG 2 | CMAQ | CML | 5299 | 019 | CML-5299(019) | CON | Millbrae Transit Center MicroMobility Hub Pilot |  |  | NEPA Clearance | 2022-11-18 | 2023-05-15 | 2022-09-06 | 2023-01-31 | 2023-01-31 | 345150 |  |  | 0 | [6 empty] | 0 |  |  | 345150 | 345150 | [6 empty] | 345150 | 345150 | [5 empty] | 2022-10-01 |  | 345150
San Mateo | Millbrae | SM-210011 | 7310 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ |  | 5299 | 018 | -5299(018) | CON | Park Blvd, San Anselmo Ave and Sta. Teresa Wy Imps |  |  | NEPA Clearance | 2022-08-31 | 2023-03-15 | 2022-06-16 | 2023-01-15 | 2023-01-31 | 347000 |  |  | 0 | [6 empty] | 0 |  |  | 347000 | 347000 | [6 empty] | 347000 | 347000 | [5 empty] | 2022-10-01 |  | 347000
San Mateo | Portola Valley | SM-170044 | 6671 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5390 | 006 | -5390(006) | CON | Portola Valley Street Preservation |  |  | NEPA Clearance | 2022-09-09 | 2023-07-24 | 2022-08-09 | 2022-12-31 | 2023-01-31 | 201000 |  |  | 0 | [6 empty] | 0 |  | 201000 |  | 201000 | [6 empty] | 201000 | 201000 | [5 empty] | 2022-10-01 |  | 201000
San Mateo | San Bruno | SM-210003 | 7244 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP | STPL | 5226 | 026 | STPL-5226(026) | CON | San Bruno Transit Corridor Ped Connection Ph4 |  |  | AC Authorized | 2022-09-13 | 2022-11-08 | 2021-11-01 | 2022-08-31 | 2023-09-30 | 385000 |  |  | 0 | [6 empty] | 0 |  | 385000 |  | 385000 | [6 empty] | 385000 | 385000 | [5 empty] | 2021-09-30 |  | 385000
San Mateo | San Bruno | SM-170017 | 6682 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ |  | 5226 | 023 | -5226(023) | CON | Huntington Transit Corridor Bike/Ped Improvements |  |  | NEPA Clearance | 2021-08-31 | 2023-07-11 | 2018-09-05 | 2023-01-31 | 2023-01-31 | 792000 |  |  | 0 | [6 empty] | 0 |  |  | 792000 | 792000 | [6 empty] | 792000 | 792000 | [5 empty] | 2022-10-01 |  | 792000
San Mateo | San Carlos | SM-090008 | 4246 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ |  | 5267 |  | -5267() | CON | US101/Holly St I/C Mod and Bike/Ped Overcrossing | [7 empty] | 2023-01-31 | 1000000 |  |  | 0 | [6 empty] | 0 |  |  | 1000000 | 1000000 | [6 empty] | 1000000 | 1000000 | 8/22 - Spoke to Matt and City is waiting for additional ATP funding and may not make FFY23 deadline. Will remmove from FFY23 AOP and will come in when ready. |  |  |  |  | 2022-10-01 |  | 1000000
San Mateo | SF City/County | SM-130031 | 6022 | STP-T4-2-PCA-REG | OBAG | STP | STPL | 6216 | 003 | STPL-6216(003) | CON | Southern Skyline Blvd. Ridge Trail Extension |  |  |  |  | 2023-07-28 | 2016-05-09 | 2023-01-31 | 2023-01-31 | 1000000 |  |  | 0 | [6 empty] | 0 |  | 1000000 |  | 1000000 | [6 empty] | 1000000 | 1000000 | [5 empty] | 2022-10-01 |  | 1000000
San Mateo | SMCCAG | SM-170046 | 6845 | RIP-T6-22-FED-SM | RTIP | RTIP-FED |  | 6419 |  | -6419() | CON | ITS Improvements in San Mateo County Northern Citi | Planned allocation | 2023-01-31 | NEPA Clearance | 2020-07-01 | 2023-05-30 |  | 2023-02-28 | 2023-01-31 | 7900000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 7900000 |  |  |  | 7900000 | 7900000 | [5 empty] | 2022-08-26 |  | 7900000
San Mateo | SMCCAG | SM-170046 | 6845 | RIP-COVID21-SM | RTIP | RTIP-FED |  | 6419 |  | -6419() | CON | ITS Improvements in San Mateo County Northern Citi | Planned allocation | 2023-01-31 | NEPA Clearance | 2020-07-01 | 2023-05-30 |  | 2023-02-28 | 2023-01-31 | 1412000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 1412000 |  |  |  | 1412000 | 1412000 | [5 empty] | 2022-08-30 |  | 1412000
San Mateo | SMCCAG | SM-110022 | 4919 | STP-T6-OBAG3-CO | OBAG 3 | STP |  | 6419 |  | -6419() | CON | San Mateo County SR2S Program |  |  | NEPA Clearance | 2022-10-31 | 2023-05-30 |  | 2023-01-31 | 2023-01-31 | 1500000 |  |  | 0 | [6 empty] | 0 |  | 1500000 |  | 1500000 | [6 empty] | 1500000 | 1500000 | 8/24 - Expect project to be approved and included in TIP by October |  |  |  |  | 2022-10-01 |  | 1500000
San Mateo | South San Francisco | SM-110003 | 4697 | RIP-T5-18-FED-SM | RTIP | RTIP-FED |  | 5177 |  | -5177() | PSE | US 101/Produce Avenue New Interchange |  |  | NEPA Clearance | 2022-10-01 |  |  | 2023-02-28 | 2023-01-31 | 5000000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 5000000 |  |  |  | 5000000 | 5000000 | [5 empty] | 2022-08-23 | 8/23 - South San Francisco received an allocation extension for this project (through 2/28/23); City anticipates requesting allocation of funds at the January 2023 CTC Meeting | 5000000
Santa Clara | Campbell | SCL210024 | 7318 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5306 | 033 | STPL-5306(033) | PE | Campbell PDA Enhancements | [5 empty] | 2022-04-22 | 2022-10-31 | 2023-01-31 | 550000 |  |  | 0 | [6 empty] | 0 |  | 550000 |  | 550000 | [6 empty] | 550000 | 550000 | 9/1 - RFA was submitted in May, but returned for for FFY22-23 submission. |  |  |  |  | 2022-10-01 |  | 550000
Santa Clara | Cupertino | SCL190036 | 7087 | CMAQ-T5-OBAG2-CO-SRTS | OBAG 2 | CMAQ | CML | 5318 | 033 | CML-5318(033) | CON | McClellan Road Separated Bikeways (Phase 3) |  |  |  |  | 2022-11-30 | 2021-09-21 | 2022-10-31 | 2023-01-31 | 1000000 |  |  | 0 | [6 empty] | 0 |  |  | 1000000 | 1000000 | [6 empty] | 1000000 | 1000000 | 9/6 - RFA was returned and addressing CalTrans Comments : E-76 Resubmittal In Progress 3/3 - Anticipate submitting RFA this month |  |  |  |  | 2021-09-30 |  | 1000000
Santa Clara | Los Gatos | SCL170028 | 6638 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ | CML | 5067 | 021 | CML-5067(021) | CON | Los Gatos Creek Trail to Hwy 9 Trailhead Connector |  |  | PS&E and PEER approved | 2022-06-30 | 2023-05-01 |  | 2023-01-31 | 2023-01-31 | 2432000 |  |  | 0 | [6 empty] | 0 |  |  | 2432000 | 2432000 | [6 empty] | 2432000 | 2432000 | [5 empty] | 2022-10-01 |  | 2432000
Santa Clara | Los Gatos | SCL170028 | 6638 | CMAQ-T5-OBAG2-CO-SRTS | OBAG 2 | CMAQ | CML | 5067 | 021 | CML-5067(021) | CON | Los Gatos Creek Trail to Hwy 9 Trailhead Connector |  |  | PS&E and PEER approved | 2022-06-30 | 2023-05-01 |  | 2023-01-31 | 2023-01-31 | 919000 |  |  | 0 | [6 empty] | 0 |  |  | 919000 | 919000 | [6 empty] | 919000 | 919000 | [5 empty] | 2022-10-01 |  | 919000
Santa Clara | Mountain View | SCL210012 | 7224 | STP-CRRSAA | OBAG 2 | CRRSAA+ | STPL | 5124 | 037 | STPL-5124(037) | CON | Mountain View - Stierlin Rd Bike-Ped Improvements |  |  |  |  | 2022-12-01 | 2021-09-02 | 2022-10-28 | 2023-09-30 | 1486000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 1486000 | 1486000 | 1486000 | [5 empty] | 2021-09-30 |  | 1486000
Santa Clara | Mountain View | SCL210012 | 7224 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP | STPL | 5124 | 037 | STPL-5124(037) | CON | Mountain View - Stierlin Rd Bike-Ped Improvements |  |  |  |  | 2022-12-01 | 2021-09-02 | 2022-10-28 | 2023-09-30 | 2521000 |  |  | 0 | [6 empty] | 0 |  | 2521000 |  | 2521000 | [6 empty] | 2521000 | 2521000 | [5 empty] | 2021-09-30 |  | 2521000
Santa Clara | MTC | SCL210022 | 7287 | STP-T5-OBAG2-REG-RSI | OBAG 2 | STP | STPLNI | 6084 | 081 | STPLNI-6084(081) | OTHER | Diridon Station Planning & Studies |  |  | RFA at CT-HQ | 2022-10-03 |  |  |  | 2023-09-30 | 1000000 |  |  | 0 | [6 empty] | 0 |  | 1000000 |  | 1000000 | [6 empty] | 1000000 | 1000000 | [5 empty] | 2021-11-04 |  | 1000000
Santa Clara | San Jose | SCL190028 | 7025 | ATP-REG-T5-4-FED | ATP-REG | ATP-FED |  | 5005 |  | -5005() | CON | Willow-Keyes Complete Streets Improvements | [7 empty] | 2023-01-31 | 12926000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 12926000 |  |  | 12926000 | 12926000 | 8/31 - Working on RFQ to procure Environmental and Design Consultant |  |  |  |  | 2022-10-01 |  | 12926000
Santa Clara | San Jose | SCL170031 | 6657 | CMAQ-T5-OBAG2-CO-SRTS | OBAG 2 | CMAQ | CML | 5005 | 156 | CML-5005(156) | CON | Mt Pleasant Ped & Bike Traffic Safety Improvements |  |  |  |  | 2023-07-01 | 2018-09-14 | 2022-11-30 | 2023-01-31 | 831793 |  |  | 0 | [6 empty] | 0 |  |  | 831793 | 831793 | [6 empty] | 831793 | 831793 | 3/15 - City submitted a revision to move to FFY23 |  |  |  |  | 2021-09-30 |  | 831793
Santa Clara | San Jose | SCL210013 | 7239 | STP-CRRSAA | OBAG 2 | CRRSAA+ | STPL | 5005 | 166 | STPL-5005(166) | CON | McKee-Julian Quick Strike Improvements |  |  |  |  | Winter 2024 | 2022-01-30 | 2023-09-30 | 2023-09-30 | 705000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 705000 | 705000 | 705000 | 8/31 - Environmental phase completed |  |  |  |  | 2021-09-30 |  | 705000
Santa Clara | San Jose | SCL210014 | 7240 | STP-CRRSAA | OBAG 2 | CRRSAA+ | STPL | 5005 | 167 | STPL-5005(167) | CON | Bascom Avenue - Quick Strike Improvements |  |  |  |  | spring 2025 | 2022-01-30 | 2024-09-30 | 2023-09-30 | 690000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 690000 | 690000 | 690000 | 8/31 - ENV in process |  |  |  |  | 2021-09-30 |  | 690000
Santa Clara | San Jose | SCL210015 | 7241 | STP-CRRSAA | OBAG 2 | CRRSAA+ | STPL | 5005 | 168 | STPL-5005(168) | CON | En Movimiento - Quick Strike Improvements |  |  |  |  | spring 2023 | 2022-01-30 | 2022-09-30 | 2023-09-30 | 1325000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 1325000 | 1325000 | 1325000 | 8/31 - Environmental phase completed |  |  |  |  | 2021-09-30 |  | 1325000
Santa Clara | San Jose | SCL210016 | 7242 | STP-CRRSAA | OBAG 2 | CRRSAA+ | STPL | 5005 | 169 | STPL-5005(169) | CON | San Jose Downtown Bikeways - Quick Strike |  |  |  |  | winter 2024 | 2022-01-30 | 2023-09-30 | 2023-09-30 | 4025000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 4025000 | 4025000 | 4025000 | 8/31 - Cultural Analysis in process |  |  |  |  | 2021-09-30 |  | 4025000
Santa Clara | San Jose | SCL170061 | 6752 | RIP-T5-18-FED-SCL | RTIP | RTIP-FED | CML | 5005 | 162 | CML-5005(162) | CON | W San Carlos Urban Village Streets Improvements | [5 empty] | 2019-09-13 | 2023-06-30 | 2023-06-30 | 4350000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 4350000 |  |  |  | 4350000 | 4350000 | 3/15 - City submitted a revision to move to FFY23 9/3 - Will require CTC extrension approval in spring 2022 8/6 - Will not deliver in FY22. Push out to FY23. |  |  |  |  | 2021-09-30 |  | 4350000
Santa Clara | San Jose | SCL170061 | 6752 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ | CML | 5005 | 162 | CML-5005(162) | CON | W San Carlos Urban Village Streets Improvements | [5 empty] | 2019-09-13 | 2023-06-30 | 2023-01-31 | 964000 |  |  | 0 | [6 empty] | 0 |  |  | 964000 | 964000 | [6 empty] | 964000 | 964000 | 8/31 - Design/env in process |  |  |  |  | 2022-10-01 |  | 964000
Santa Clara | San Jose | SCL210026 | 7321 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5005 |  | -5005() | PE | Julian and St. James Couplet Conversion | [5 empty] | 2022-09-30 | 2022-10-31 | 2023-01-31 | 2067572 |  |  | 0 | [6 empty] | 0 |  | 2067572 |  | 2067572 | [6 empty] | 2067572 | 2067572 | 8/31 - Funds awarded 11/21 |  |  |  |  | 2022-10-01 |  | 2067572
Santa Clara | Saratoga | SCL170054 | 6664 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5332 | 024 | STPL-5332(024) | CON | Saratoga Village Crosswalks and Sidewalk Rehab | RFA by end of June | 2022-06-22 | RFA at CT-District | 2022-08-20 | 2023-05-01 | 2021-10-12 | 2022-11-30 | 2023-01-31 | 338000 |  |  | 0 | [6 empty] | 0 |  | 338000 |  | 338000 | [6 empty] | 338000 | 338000 | 8/29 - State out of OA and City will resubmit RFA begiining of next FFY. 6/22 - City plans to submit RFA by end of June 2022 9/15 - City to submit FR request and docs to CT this week. 9/15/21 - Request for FR info. |  |  |  |  | 2021-09-30 |  | 338000
Santa Clara | Sunnyvale | SCL170017 | 6555 | ATP-ST-T5-3-FED | ATP-ST | ATP-FED | ATPL | 5213 | 068 | ATPL-5213(068) | CON | Sunnyvale SNAIL Neighborhood Improvements |  |  | CTC Approved PE | 2022-05-19 |  | 2022-01-04 | 2023-01-31 | 2023-01-31 | 3982000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 3982000 |  |  | 3982000 | 3982000 | 8/27 - Construction funding deferred to FY2023 3/23 - Requesting Extension to FY21 at May meeting |  |  |  |  | 2022-10-01 |  | 3982000
Santa Clara | Sunnyvale | SCL210023 | 7300 | STP-CRRSAA | OBAG 2 | CRRSAA+ | STPL | 5213 | 074 | STPL-5213(074) | CON | Sunnyvale Bicycle, Pedestrian and SRTS Safety Imps |  |  | ROW cert approved | 2022-08-22 | 2022-05-31 | 2022-04-29 | 2022-09-30 | 2023-09-30 | 1900000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 1900000 | 1900000 | 1900000 | [5 empty] | 2021-09-30 |  | 1900000
Santa Clara | Sunnyvale | SCL170022 | 6566 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ | CML | 5213 | 064 | CML-5213(064) | PE | Java Dr Road Diet and Bike Lanes | [5 empty] | 2021-08-27 |  | 2023-01-31 | 157212 |  | 128788 | 128788 | [6 empty] | 128788 |  |  | 286000 | 286000 | [6 empty] | 286000 | 157212 | 3/3 - Will obligate funds after TIP amendment. Maybe May/June 9/3 - City is working on Inactive Obligations and would like to remove PE funds to CON. Requested to move unobligated PE funding into Construction |  |  |  |  | 2020-09-30 |  | 286000
Santa Clara | Sunnyvale | SCL170020 | 6620 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ | CML | 5213 |  | CML-5213() | PE | Bernardo Avenue Bicycle Underpass |  |  | FR in progress |  |  | 2022-10-31 | 2023-01-31 | 2023-01-31 | 500000 |  |  | 0 | [6 empty] | 0 |  |  | 500000 | 500000 | [6 empty] | 500000 | 500000 | [5 empty] | 2022-10-01 |  | 500000
Santa Clara | Sunnyvale | SCL170023 | 6613 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ | CML | 5213 | 061 | CML-5213(061) | CON | Peery Park "Sense of Place" Improvements |  |  | FL issued for PE | 2018-09-06 |  | 2022-07-22 | 2023-01-31 | 2023-01-31 | 2329000 |  |  | 0 | [6 empty] | 0 |  |  | 2329000 | 2329000 | [6 empty] | 2329000 | 2329000 | [5 empty] | 2022-10-01 |  | 2329000
Solano | Fairfield | SOL210001 | 7182 | STP-T5-OBAG2-CO | OBAG 2 | STP |  | 5132 |  | -5132() | CON | Fairfield - Cadenasso Drive Paving |  |  |  |  | 2023-04-04 | 2022-06-01 | 2023-01-15 | 2023-01-31 | 1394000 |  |  | 0 | [6 empty] | 0 |  | 1394000 |  | 1394000 | [6 empty] | 1394000 | 1394000 | [5 empty] | 2022-10-01 |  | 1394000
Solano | Fairfiled | SOL170006 | 6536 | ATP-ST-T5-3-FED | ATP-ST | ATP-FED |  | 5132 | 047 | -5132(047) | CON | East Tabor Tolenas SR2S Sidewalk Gap Closure |  |  |  |  | 2023-04-04 | 2017-11-29 | 2023-01-15 | 2023-01-31 | 1440000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  |  | 1440000 |  |  | 1440000 | 1440000 | [5 empty] | 2022-10-01 |  | 1440000
Solano | STA | SOL110019 | 6270 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 5030 |  | -5030() | CON | Solano Safe Routes to School Program |  |  |  |  | 2022-11-15 | N/A | 2022-10-01 | 2023-09-30 | 600000 |  |  | 0 | [6 empty] | 0 |  | 600000 |  | 600000 | [6 empty] | 600000 | 600000 | [5 empty] | 2021-09-30 |  | 600000
Solano | STA | SOL110006 | 4313 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ |  | 5030 | 069 | -5030(069) | CON | Jepson: Leisure Town Road Phase 1B and 1C |  |  |  |  | 2023-05-01 | 2019-04-29 | 2023-01-31 | 2023-01-31 | 1407000 |  |  | 0 | [6 empty] | 0 |  |  | 1407000 | 1407000 | [6 empty] | 1407000 | 1407000 | [5 empty] | 2022-10-01 |  | 1407000
Solano | STA | SOL110006 | 4313 | EARMARK-T5-RE | EARMARK | EARMARK |  | 5030 | 069 | -5030(069) | CON | Jepson: Leisure Town Road Phase 1B and 1C |  |  |  |  | 2023-05-01 | 2019-04-29 | 2023-01-31 | 2023-09-30 | 81047 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 | [5 empty] | 81047 | 81047 | 81047 | [5 empty] | 2022-10-01 |  | 81047
Solano | Vacaville | SOL110006 | 4313 | RIP-T4-12-FED-SOL | RTIP | RTIP-FED | RSTPLR | 5094 | 069 | RSTPLR-5094(069) | CON | Jepson: Leisure Town Road Phase 1B and 1C |  | Jan/Feb 2022 | Finalizing ROW Acq. |  | 2022-04-12 | 2019-04-29 | 2022-01-14 | 2022-06-30 | 3296000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 3296000 |  |  |  | 3296000 | 3296000 | 6/25 - Project confirmed by Tracy |  |  |  |  | 2021-09-30 |  | 3296000
Solano | Vacaville | SOL110006 | 4313 | RIP-T5-18-FED-SOL | RTIP | RTIP-FED | RSTPLR | 5094 | 069 | RSTPLR-5094(069) | CON | Jepson: Leisure Town Road Phase 1B and 1C |  | Jan/Feb 2022 | Finalizing ROW Acq. |  | 2022-04-12 | 2019-04-29 | 2022-01-14 | 2022-06-30 | 6000000 |  |  | 0 | [6 empty] | 0 |  |  |  | 0 |  |  | 6000000 |  |  |  | 6000000 | 6000000 | 6/25 - Project confirmed by Tracy |  |  |  |  | 2021-09-30 |  | 6000000
Solano | Vacaville | SOL170013 | 6686 | CMAQ-T5-OBAG2-CO | OBAG 2 | CMAQ |  | 5094 |  | -5094() | CON | Vaca Valley/I505 Multimodal Improvements | [7 empty] | 2023-01-31 | 1907000 |  |  | 0 | [6 empty] | 0 |  |  | 1907000 | 1907000 | [6 empty] | 1907000 | 1907000 | 8/29 - Requesting to reprogram to Jepson: Leisure Town Road Phase 1B/1C |  |  |  |  | 2022-10-01 |  | 1907000
Solano | Vacaville | SOL210002 | 7209 | STP-T5-OBAG2-REG-HIP | OBAG 2 | STP |  | 5094 |  | -5094() | CON | Vacaville Pavement Preservation |  |  |  |  | 2023-05-01 | 2021-10-14 | 2023-01-31 | 2023-01-31 | 1900000 |  |  | 0 | [6 empty] | 0 |  | 1900000 |  | 1900000 | [6 empty] | 1900000 | 1900000 | [5 empty] | 2022-10-01 |  | 1900000
Solano | Vallejo | SOL210020 | 7332 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP |  | 5030 |  | -5030() | CON | Vallejo Springs Rd Pavement Preservation |  |  | Field Review and PES Submittal | 2022-07-14 | 2023-05-01 | 2022-06-29 | 2023-02-01 | 2023-09-30 | 1800000 |  |  | 0 | [6 empty] | 0 |  | 1800000 |  | 1800000 | [6 empty] | 1800000 | 1800000 | 3/1 - Exchange from SOL170008 |  |  |  |  | 2022-03-01 |  | 1800000
Solano | Vallejo | SOL210007 | 7316 | CMAQ-T5-OBAG2-REG-CI | OBAG 2 | CMAQ |  | 5030 |  | -5030() | CON | Vallejo Ferry Mobility Hub Improvement |  |  | Field Review and PES Submittal | 2022-07-21 | 2023-04-01 | 2022-07-21 | 2023-01-31 | 2023-01-31 | 200000 |  |  | 0 | [6 empty] | 0 |  |  | 200000 | 200000 | [6 empty] | 200000 | 200000 | [5 empty] | 2022-10-01 |  | 200000
Sonoma | Cotati | SON210002 | 7226 | STP-T5-OBAG2-REG-SSM | OBAG 2 | STP | STPL | 5383 | 014 | STPL-5383(014) | CON | Cotati Downtown-Civic Center Connectivity Safety |  |  | AC Authorized | 2022-09-20 | 2023-03-14 | 2021-12-21 | 2022-09-30 | 2023-09-30 | 242000 |  |  | 0 | [6 empty] | 0 |  | 242000 |  | 242000 | [6 empty] | 242000 | 242000 | 8/23 - City confirmed project for FFY21/22, possibly early 2022. Need to follow up with FR |  |  |  |  | 2021-09-30 |  | 242000
Sonoma | Sebastopol | SON170021 | 6607 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5123 | 016 | STPL-5123(016) | CON | Bodega Avenue Bike Lanes and Pavement Rehab |  |  |  |  | 2023-04-01 | 2021-06-09 | 2022-11-01 | 2023-01-31 | 1195000 |  |  | 0 | [6 empty] | 0 |  | 1195000 |  | 1195000 | [6 empty] | 1195000 | 1195000 | [5 empty] | 2022-10-01 |  | 1195000
Sonoma | Son Co Reg Park | SON170025 | 6600 | STP-T5-OBAG2-REG-PCA | OBAG 2 | STP | STPL | 5920 | 164 | STPL-5920(164) | CON | Joe Rodota Trail Bridge Replacement |  |  | NEPA Clearance | 2022-09-30 | 2023-05-09 | 2019-05-01 | 2023-01-31 | 2023-01-31 | 529000 |  |  | 0 | [6 empty] | 0 |  | 529000 |  | 529000 | [6 empty] | 529000 | 529000 | [5 empty] | 2022-10-01 |  | 529000
Sonoma | Son Co TA | SON170009 | 6505 | STP-T6-OBAG3-CO | OBAG 3 | STP |  | 6364 | 021 | -6364(021) | OTHER | Sonoma County - County-Wide SRTS Program |  |  |  |  | 2023-05-30 |  | 2023-01-15 | 2023-01-31 | 1910000 |  |  | 0 | [6 empty] | 0 |  | 1910000 |  | 1910000 | [6 empty] | 1910000 | 1910000 | [5 empty] | 2022-10-01 |  | 1910000
Sonoma | Sonoma County | SON170014 | 6624 | STP-T5-OBAG2-CO | OBAG 2 | STP | STPL | 5920 | 175 | STPL-5920(175) | CON | Crocker Bridge Bike and Pedestrian Passage |  |  | NEPA Clearance | 2022-09-15 | 2023-04-07 | 2021-05-07 | 2023-01-31 | 2023-01-31 | 1145000 |  |  | 0 | [6 empty] | 0 |  | 1145000 |  | 1145000 | [6 empty] | 1145000 | 1145000 | [5 empty] | 2022-10-01 |  | 1145000
Sonoma | Sonoma County | SON170014 | 6624 | STP-T5-OBAG2-REG-PCA | OBAG 2 | STP | STPL | 5920 | 175 | STPL-5920(175) | CON | Crocker Bridge Bike and Pedestrian Passage |  |  | NEPA Clearance | 2022-09-15 | 2023-04-07 | 2021-05-07 | 2023-01-31 | 2023-01-31 | 1280000 |  |  | 0 | [6 empty] | 0 |  | 1280000 |  | 1280000 | [6 empty] | 1280000 | 1280000 | [5 empty] | 2022-10-01 |  | 1280000
[10 empty] | -() | [9 empty] | 2023-01-31 | 0
[21 empty] | 320192200.0221 | 0 | 128788 | 128788 | 0 | 3753672 | 0 | 0 | 0 | 0 | 3882460 | 0 | 121983874 | 63735710 | 185719584 | 7426700 | 41158245.4821 | 31001238 | 32234000 | 0 | 26534892.54 | 324074660.0221 | 320192200.0221 | [7 empty] | 324074660.0221
J:\PROJECT\Funding\T5-FAST\STP-CMAQ\Obligations and Delivery\Annual Obligation Plans\FY 2022-23\[MTC FFY22-23 Annual Obligation Plan.xlsx]FFY 2022-23 Oct 31 |  | J:\170005 |  |  | 142 | [27 empty] | -10391376 | 9054865 | -1336511
Brought over from FFY21/22 | [23 empty] | 106856993
Remove from FFY21/22 AOP | [20 empty] | 2006820 |  | #REF! | 106728205
Confirmed for FFY22/23 | [22 empty] | 25000000 | [19 empty] | 12/13 - SJ needs to work with MTC on TIP Revision
Sponsor has requested to remove and/or not responded and will remove upon final submission to CT | [19 empty] | #REF! | #REF! | #REF! | #REF! | #REF!
Wants to move out, but needs to address Inactive Obligations for TIP programming change. | [22 empty] | 128788
Follow up for FR, Award date, SPOC, HPMS, or more info by 9/23 | [22 empty] | #REF!
Extension CTC extension request/approval | [20 empty] | #REF! |  | #REF!
Missed delivery in FFY21/22
S&S Mobility QS not in FMS
Need HPMS reporting | Need HPMS reporting | [17 empty] | #REF! |  |  |  | #REF!
Allocated but needs obligation
Project completed | [22 empty] | #REF!
Move out to FFY23-24 if Commission approves OBAG 2 program extension.
123556965
[21 empty] | #REF! | #REF! | #REF! | #REF!
#REF!
Note on N17: John Saelee: 8/31 - Duration of Caltrans Encroachment Permit review is the main risk to project delivery schedule. Staff anticipates ROW date of completion sometime next month with design completion following shortly after that (still waiting on final Caltrans comments on the encroachment permit for any last changes). Sponsor confirmed Surplus Lands Act resolution is scheduled for September 6.
Note on N18: John Saelee: Project is currently on schedule. Potential risks include schedule for NEPA clearance and finalizing design (including utility coordination), as well as uncertainty in construction costs (inflation).
Note on N19: John Saelee: Project is currently on schedule. Potential risks include schedule for NEPA clearance and finalizing design (including utility coordination), as well as uncertainty in construction costs (inflation).
Note on N24: John Saelee: 8/31 - These funds have been reprogrammed to SR2S, ALA110033; $620K of which will be obligated in 22-23 with $1.5M SSM SR2S. Funds are actually programmed in FFY23/24. TIP revision needed to reprogram funds to FFY23.
Note on W28: John Saelee: 6/28 - Partial obligation?
Note on N29: John Saelee: 8/31 - Sponsor confirmed Surplus Lands Act resolution is scheduled for September.
Note on D31: John Saelee: CCTA will work with MTC staff to see if the Study can be funded through FTA and therefore not have to go to DLAE. FTA transfer will be completed before 9/30/22.
Note on T48: John Saelee: The Pavement Project already had the Field Review and was nearing getting NEPA clearance. With the addition of Cycle Track, they have to do a quick revision. They have already spoken to CT DLAE.
Note on T50: John Saelee: The Pavement Project already had the Field Review and was nearing getting NEPA clearance. With the addition of Cycle Track, they have to do a quick revision. They have already spoken to CT DLAE.
Note on W53: John Saelee: 9/16/21 - Obligated $506,812.49 on MRN970016. Balance of $887,051.51 will be reprogrammed to MRN050018 in Nov/Dec TIP Revision.
Note on L79: John Saelee: 8/31 - Please note that historically, Caltrans recognized these projects as separate bridge projects. At SFCTA's request, Caltans closed out the various federal-aid projects and combined them into a new project number, STPLZ-6272(046). Attachment 5 includes the E-76 authorization approved in November 2018. Although we are no longer billing to the various projects listed on the FFY22-23 Annual Obligation Plan spreadsheet, Caltrans has still requested SFCTA to continuously submit State Prop 1B progress reports by allocating costs incurred under the new combined project STPLZ-6272(046) proportionally to the 8 bridges.
Note on L80: John Saelee: 8/31 - Please note that historically, Caltrans recognized these projects as separate bridge projects. At SFCTA's request, Caltans closed out the various federal-aid projects and combined them into a new project number, STPLZ-6272(046). Attachment 5 includes the E-76 authorization approved in November 2018. Although we are no longer billing to the various projects listed on the FFY22-23 Annual Obligation Plan spreadsheet, Caltrans has still requested SFCTA to continuously submit State Prop 1B progress reports by allocating costs incurred under the new combined project STPLZ-6272(046) proportionally to the 8 bridges.
Note on L81: John Saelee: 8/31 - Please note that historically, Caltrans recognized these projects as separate bridge projects. At SFCTA's request, Caltans closed out the various federal-aid projects and combined them into a new project number, STPLZ-6272(046). Attachment 5 includes the E-76 authorization approved in November 2018. Although we are no longer billing to the various projects listed on the FFY22-23 Annual Obligation Plan spreadsheet, Caltrans has still requested SFCTA to continuously submit State Prop 1B progress reports by allocating costs incurred under the new combined project STPLZ-6272(046) proportionally to the 8 bridges.
Note on L82: John Saelee: 8/31 - Please note that historically, Caltrans recognized these projects as separate bridge projects. At SFCTA's request, Caltans closed out the various federal-aid projects and combined them into a new project number, STPLZ-6272(046). Attachment 5 includes the E-76 authorization approved in November 2018. Although we are no longer billing to the various projects listed on the FFY22-23 Annual Obligation Plan spreadsheet, Caltrans has still requested SFCTA to continuously submit State Prop 1B progress reports by allocating costs incurred under the new combined project STPLZ-6272(046) proportionally to the 8 bridges.
Note on L83: John Saelee: 8/31 - Please note that historically, Caltrans recognized these projects as separate bridge projects. At SFCTA's request, Caltans closed out the various federal-aid projects and combined them into a new project number, STPLZ-6272(046). Attachment 5 includes the E-76 authorization approved in November 2018. Although we are no longer billing to the various projects listed on the FFY22-23 Annual Obligation Plan spreadsheet, Caltrans has still requested SFCTA to continuously submit State Prop 1B progress reports by allocating costs incurred under the new combined project STPLZ-6272(046) proportionally to the 8 bridges.
Note on L84: John Saelee: 8/31 - Please note that historically, Caltrans recognized these projects as separate bridge projects. At SFCTA's request, Caltans closed out the various federal-aid projects and combined them into a new project number, STPLZ-6272(046). Attachment 5 includes the E-76 authorization approved in November 2018. Although we are no longer billing to the various projects listed on the FFY22-23 Annual Obligation Plan spreadsheet, Caltrans has still requested SFCTA to continuously submit State Prop 1B progress reports by allocating costs incurred under the new combined project STPLZ-6272(046) proportionally to the 8 bridges.
Note on L85: John Saelee: 8/31 - Please note that historically, Caltrans recognized these projects as separate bridge projects. At SFCTA's request, Caltans closed out the various federal-aid projects and combined them into a new project number, STPLZ-6272(046). Attachment 5 includes the E-76 authorization approved in November 2018. Although we are no longer billing to the various projects listed on the FFY22-23 Annual Obligation Plan spreadsheet, Caltrans has still requested SFCTA to continuously submit State Prop 1B progress reports by allocating costs incurred under the new combined project STPLZ-6272(046) proportionally to the 8 bridges.
Note on L86: John Saelee: 8/31 - Please note that historically, Caltrans recognized these projects as separate bridge projects. At SFCTA's request, Caltans closed out the various federal-aid projects and combined them into a new project number, STPLZ-6272(046). Attachment 5 includes the E-76 authorization approved in November 2018. Although we are no longer billing to the various projects listed on the FFY22-23 Annual Obligation Plan spreadsheet, Caltrans has still requested SFCTA to continuously submit State Prop 1B progress reports by allocating costs incurred under the new combined project STPLZ-6272(046) proportionally to the 8 bridges.
Note on L87: John Saelee: 8/31 - Please note that historically, Caltrans recognized these projects as separate bridge projects. At SFCTA's request, Caltans closed out the various federal-aid projects and combined them into a new project number, STPLZ-6272(046). Attachment 5 includes the E-76 authorization approved in November 2018. Although we are no longer billing to the various projects listed on the FFY22-23 Annual Obligation Plan spreadsheet, Caltrans has still requested SFCTA to continuously submit State Prop 1B progress reports by allocating costs incurred under the new combined project STPLZ-6272(046) proportionally to the 8 bridges.
Note on L88: John Saelee: 8/31 - Please note that historically, Caltrans recognized these projects as separate bridge projects. At SFCTA's request, Caltans closed out the various federal-aid projects and combined them into a new project number, STPLZ-6272(046). Attachment 5 includes the E-76 authorization approved in November 2018. Although we are no longer billing to the various projects listed on the FFY22-23 Annual Obligation Plan spreadsheet, Caltrans has still requested SFCTA to continuously submit State Prop 1B progress reports by allocating costs incurred under the new combined project STPLZ-6272(046) proportionally to the 8 bridges.